🦆

QUACK-FOCUS

Agentic Focus OS — Full Product & Build Documentation

Hackathon Sprint · v1.0 · Team Internal

# 0.  Quick Reference & Contacts

| Name / Role | Key Responsibility | Primary Stack | Slack / Contact |
| --- | --- | --- | --- |
| Karan — Creative Dir. | 3D Assets, Garden, UX | Three.js, Blender, Next.js | @karan |
| Dev A — Systems Arch. | Electron, Chrome Ext. | Electron, JS, CSS Inject | @devA |
| Dev B — Backend/RT | Server, DB, AI | Node, Socket.io, MongoDB | @devB |

🏁 Hackathon Goal Ship a working MVP that feels like a real product — not a demo. Every feature should be demo-able live in under 30 seconds. If it can't be shown on screen, it doesn't exist at the hackathon.

# 1.  Vision & Product Positioning

## 1.1  The One-Liner

Quack-Focus is a living desktop companion that rewards deep work and punishes distraction — in real time, with AI-powered sass.

## 1.2  The Problem We're Solving

The attention economy is winning. Traditional productivity apps (timers, blockers) are passive — they only react after the fact or require the user to care about them. There is no tool that actively fights back.

## 1.3  Our Unique Insight

💡 Core Insight Accountability works best when it's social, visible, and slightly embarrassing. The Duck is a persistent character that makes your focus state public — first to yourself, then to your team. It transforms a private habit into a social one.

## 1.4  The Three Pillars

| 🔴 The Stick | 🥕 The Carrot | 👥 The Social |
| --- | --- | --- |
| The Duck blurs your screen, steals your cursor, and roasts you with AI when you drift to distracting sites. | Every focus session grows a 3D Productivity Garden. 25 mins = new plant. 10 mins of slacking = plant dies. | Squad Mode lets teammates see your Duck status in real time and trigger a Ghost Duck roast if you're slacking. |

## 1.5  Competitive Differentiation

How we compare to existing tools:

| Tool | Active Punishment | 3D Reward | Multiplayer | AI Roasts |
| --- | --- | --- | --- | --- |
| Forest | ✗ | ✗ | Partial | ✗ |
| Cold Turkey | Partial | ✗ | ✗ | ✗ |
| Desktop Gremlin | Partial | ✗ | ✗ | ✗ |
| Quack-Focus ✦ | ✅ | ✅ | ✅ | ✅ |

## 1.6  Go-To-Market (Post-Hackathon)

Target Segments:

- Tier 1 — Remote dev teams (10-50 people) already using tools like Linear, Notion, Slack

- Tier 2 — Students / solo devs who want gamified accountability

- Tier 3 — Twitch/YouTube productivity streamers (the Duck is inherently content-friendly)

Monetization Model:

- Free tier: Duck + 1 garden plot, solo mode only

- Pro tier ($5/mo): Full garden, custom Duck skins, unlimited sessions

- Squad tier ($8/user/mo): Full Squad Mode, Ghost Duck triggers, team analytics dashboard

# 2.  Product Features (Detailed Spec)

## 2.1  The Chaos Duck — Desktop Presence

The core product differentiator. Inspired by Desktop Gremlin — a persistent 3D character that lives outside browser windows and reacts to system-level state.

### States & Behavior

| State | Trigger | Duck Behavior | Screen Effect | Exit |
| --- | --- | --- | --- | --- |
| 🟢 Idle | No tab open | Sits on taskbar, bobs head | None | Automatic |
| 🔵 Focus | GitHub/VSCode/Docs active | Waters garden, happy walk | Subtle glow on Duck | Automatic |
| 🟡 Warning | 1-5 min on distraction | Paces, stares at user | Slight blur (10%) | Close tab |
| 🔴 Chaos | >5 min on distraction | Runs at screen, bites cursor | Heavy blur + roast bubble | Pet for 10 sec |
| 👻 Ghost Duck | Squad triggers roast | Ghost overlay quacks loudly | Full-screen flash | Auto-dismiss 30s |

### The 'Blur of Shame' — Implementation Detail

The blur escalates as distraction time increases. It is never a hard block (to avoid legal/accessibility issues), but it becomes irritating enough that focusing is easier than continuing.

- 0-1 min: No effect

- 1-3 min: blur(2px) applied via CSS filter injection

- 3-5 min: blur(6px) + slight desaturate(50%)

- >5 min: blur(12px) + grayscale(80%) + Duck enters Chaos state

⚠️ Technical Note for Dev A The Blur must be applied at the Electron shell level, NOT inside the extension. The extension can only blur its own iframe. Electron's BrowserWindow can overlay a transparent, click-through window with a CSS backdrop-filter that covers ALL apps. This is the key architectural decision.

### The 'Petting' Reset

To cancel Chaos mode, the user must hover the mouse over the Duck for 10 continuous seconds. A progress ring animates around the Duck. This is a deliberate friction point — it forces the user to consciously commit to refocusing rather than just closing a popup.

- If mouse leaves during the 10s: reset progress to 0

- On success: Duck does a happy animation, blur clears, focus timer restarts

- AI quip plays on completion: e.g. 'Fine. I forgive you. Don't make me do that again.'

## 2.2  The Productivity Garden

A persistent, growing 3D world that visualizes accumulated focus. This is the emotional core of the carrot mechanism.

### Growth Rules

| Event | Duration | Garden Effect | Asset |
| --- | --- | --- | --- |
| Focus Session | 25 min | Spawn small flower | flower_01.glb |
| Focus Session | 50 min | Spawn tree (small) | tree_01.glb |
| Focus Session | 90 min | Spawn large tree + glow | tree_02.glb |
| Distraction | >10 min | Duck eats 1 plant | Eat animation |
| Squad Roast Sent | Any | Golden Duck trophy | trophy.glb |

### Technical Notes

- Garden persists in MongoDB per user. On dashboard load, re-hydrate all placed objects with their positions.

- Use instanced meshes (Three.js InstancedMesh) for plants — do NOT create individual Mesh per plant or performance degrades past ~50 plants.

- Floating island base mesh can be a simple stylized asset — priority is the plants being visually rewarding, not the terrain.

- Add a day/night cycle driven by local time — subtle atmospheric effect, no gameplay impact.

## 2.3  Squad Mode (Multiplayer Accountability)

🚀 This is the most demo-able feature at the hackathon. When you trigger a Ghost Duck on a teammate's screen live on stage, the audience will react. Build this to work reliably even if everything else is rough.

### Flow Diagram (Text)

User A joins a Squad → User B joins same Squad code → Socket.io rooms bind them together → User A's Chrome Extension detects YouTube → Server broadcasts A's status as 'SLACKING' → User B sees A's duck icon go red in the Squad panel → User B clicks 'Send Ghost Duck' → Server emits GHOST_DUCK event to User A's Electron → User A sees full-screen Ghost Duck + hears quack SFX + gets AI roast

### The Snitch Mechanic — What Gets Shared

- Focus status: Focusing / Idle / Slacking (no raw URL shared for privacy)

- Current app category: Coding / Docs / Entertainment / Social / Other

- Focus streak: Current unbroken focus minutes

- Garden preview: Thumbnail of teammate's garden

🔒 Privacy Note Never share exact URLs between users. Only share categories (e.g. 'Entertainment'). This is both a privacy best practice and a legal safeguard. The AI roast can reference the category generically: 'Watching videos again, huh?'

# 3.  Technical Architecture

## 3.1  System Overview

Quack-Focus is a hybrid architecture — four components that communicate in real time. Each component has a clear, single responsibility.

| Layer | Technology | Responsibility | Connects To |
| --- | --- | --- | --- |
| Dashboard | Next.js 14 + Three.js | 3D Garden, Analytics, Squad Panel | Socket.io server, MongoDB |
| Desktop Duck | Electron + Three.js | Transparent overlay, Duck rendering, Blur logic, Ghost Duck | Socket.io server |
| Browser Sensor | Chrome Extension (MV3) | URL detection, Tab state, Focus classification | Socket.io server |
| Server / RT | Node.js + Socket.io + MongoDB | Central event bus, Squad rooms, AI roast gen, Data persistence | All other layers |

## 3.2  Communication Protocol

All real-time events flow through Socket.io. Below are the events that must be implemented for the MVP.

| Event Name | Emitter | Listener | Payload |
| --- | --- | --- | --- |
| tab:update | Extension | Server | { userId, category, isDistraction, timestamp } |
| duck:state | Server | Electron | { state: "idle"¦"focus"¦"warn"¦"chaos" } |
| squad:status | Server | Dashboard | { userId, state, streak, category } |
| squad:ghost | Dashboard | Server→Electron | { targetUserId, roastText } |
| garden:update | Server | Dashboard | { userId, action: "add"¦"remove", asset, position } |

## 3.3  MongoDB Schema

### Users Collection

- _id, email, username, squadId, createdAt

- stats: { totalFocusMinutes, totalSlackMinutes, longestStreak, currentStreak }

- garden: [ { assetId, position: {x,y,z}, spawnedAt } ]

### Sessions Collection

- _id, userId, type: 'focus'|'slack', startedAt, endedAt, durationMinutes

- category (for slack sessions): 'social', 'entertainment', 'news', 'other'

### Squads Collection

- _id, name, code (6-char invite code), members: [userId], createdAt

- roasts: [ { fromUserId, toUserId, text, sentAt } ] — last 50 only

## 3.4  Chrome Extension Architecture (MV3)

The extension is the 'sensor' layer. It should be lightweight and fast. Do not put business logic here.

- manifest.json: Declare permissions — tabs, webNavigation, storage, host_permissions for socket server

- background.js (Service Worker): Listen to chrome.tabs.onActivated and chrome.webNavigation.onCommitted

- Maintain a local lookup table of distracting domains → category (e.g. youtube.com → entertainment)

- Debounce tab events — emit to server only if user stays on the same domain for >5 seconds

- Send heartbeat every 30s to keep session alive

⚠️ MV3 Constraint Chrome Extension Manifest V3 Service Workers terminate after ~30s of inactivity. Use chrome.alarms API to keep the heartbeat alive, not setInterval. This is a common hackathon gotcha.

## 3.5  Electron Window Configuration

The Duck window must be transparent, always-on-top, and not steal focus from the user's work.

- frame: false, transparent: true, alwaysOnTop: true

- skipTaskbar: true — the Duck should not appear in the taskbar as a separate window

- Default: setIgnoreMouseEvents(true, { forward: true }) — click-through mode so the Duck doesn't interfere with work

- In Chaos mode: setIgnoreMouseEvents(false) — Duck intercepts mouse to enable 'petting' reset

- Use screen.getAllDisplays() to support multi-monitor setups

💡 Improvement Suggestion Add a system tray icon (Tray API) so users can right-click to pause the Duck, switch focus modes, or quit. This makes the product feel polished and is a major quality-of-life feature. Estimated: 1 hour for Dev A.

# 4.  Master To-Do List — 15-Hour Sprint

🎯 How to Use This List Each task has an owner, an estimated time, a phase, and a priority (P0 = must ship, P1 = should ship, P2 = nice to have). Do P0s before touching anything else. Update the status column in your copy as you go.

## Phase 1 — Foundation (Hours 0–4)

Goal: Every team member has a working, connected skeleton. No features, just scaffolding that talks.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Set up Next.js 14 repo, Tailwind, basic routing (/, /dashboard, /squad) | Karan | 45 min | P0 |
| Import Duck GLB into Three.js scene — verify it loads with idle animation | Karan | 60 min | P0 |
| Set up basic Three.js island scene (plane + sky) in Next.js dashboard | Karan | 45 min | P0 |
| Create Electron app — transparent always-on-top window, 'Hello Duck' on screen | Dev A | 45 min | P0 |
| Render the Duck GLB inside the Electron window with basic idle animation | Dev A | 60 min | P0 |
| Set up Chrome Extension MV3 skeleton — log tab changes to console | Dev A | 30 min | P0 |
| Set up Node.js + Express + Socket.io server — deploy to Railway or Render | Dev B | 45 min | P0 |
| Define MongoDB schemas (Users, Sessions, Squads) — connect Mongoose | Dev B | 45 min | P0 |
| Extension emits tab:update to server — server logs it in console | Dev B | 30 min | P0 |
| Electron app connects to Socket.io server — receives test ping | Dev A | 20 min | P0 |

## Phase 2 — Core Logic (Hours 5–9)

Goal: The Duck reacts to real behavior. The Garden grows. The Squad panel shows live status.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Implement Duck state machine (Idle→Focus→Warn→Chaos) in Electron via socket events | Dev A | 90 min | P0 |
| Switch Duck GLB animation based on state (idle anim, walk anim, bite anim) | Karan | 60 min | P0 |
| Implement CSS blur injection in Electron — escalating blur levels per state | Dev A | 45 min | P0 |
| Build domain-to-category lookup in Extension — detect distracting vs. focus sites | Dev A | 30 min | P0 |
| Server-side: compute user state from tab:update events + emit duck:state to Electron | Dev B | 60 min | P0 |
| Server-side: track focus time, slack time, update session records in MongoDB | Dev B | 45 min | P0 |
| Garden: on session complete event, spawn a new plant asset in Three.js scene | Karan | 60 min | P0 |
| Garden: load persisted plants from MongoDB on dashboard load | Dev B + Karan | 45 min | P0 |
| Squad: implement room join/leave via invite code — Socket.io rooms | Dev B | 45 min | P0 |
| Squad: Dashboard panel shows all squad members + their current Duck state | Karan | 60 min | P1 |
| Implement 'Pet to Reset' interaction — 10s hover progress ring on Duck | Dev A | 45 min | P1 |

## Phase 3 — The 'Wow' Factors (Hours 10–13)

Goal: The features that will win the hackathon. Every item here must work on demo day.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| Integrate Gemini API — generate roast text based on distraction category + streak | Dev B | 60 min | P0 |
| Render AI roast text in speech bubble on Duck (Electron canvas overlay) | Dev A | 45 min | P0 |
| Ghost Duck: when squad:ghost event received, show Ghost Duck overlay + play quack SFX | Dev A | 60 min | P0 |
| Squad panel: 'Send Roast' button — triggers squad:ghost event to target user | Karan | 30 min | P0 |
| Add quack sound effect when Duck enters Chaos mode (Web Audio API in Electron) | Dev A | 20 min | P1 |
| Garden: plant 'eaten' animation when Duck removes a plant (slack >10 min) | Karan | 45 min | P1 |
| Focus analytics card — today's focus time, streak, plants grown (in dashboard) | Karan | 45 min | P1 |
| Add system tray icon with Pause/Resume and Quit options | Dev A | 45 min | P1 |
| Duck skins: at least 2 alternate Duck color variants (swap material/texture on GLB) | Karan | 30 min | P2 |
| Smooth camera auto-pan in garden as new plants spawn | Karan | 30 min | P2 |
| Leaderboard widget in Squad panel (most focus minutes this week) | Dev B | 45 min | P2 |

## Phase 4 — Polish & Demo Prep (Hours 14–15)

Goal: The product must survive a live demo. Hardcode fallbacks if anything is flaky.

| Task | Owner | Est. | Priority |
| --- | --- | --- | --- |
| End-to-end test: Extension detects YouTube → Duck goes Chaos → Roast fires | All | 30 min | P0 |
| End-to-end test: Squad Ghost Duck trigger across two machines | All | 30 min | P0 |
| Add pre-seeded garden with ~10 plants so demo looks lush on day one | Dev B | 15 min | P0 |
| Add a 'Demo Mode' hotkey that immediately triggers Chaos state (for presentations) | Dev A | 20 min | P0 |
| Record 90-second screen capture demo video as backup | Karan | 30 min | P0 |
| Write a 5-slide pitch deck: Problem → Solution → Demo → Market → Ask | All | 30 min | P0 |
| UI pass: consistent dark-mode color palette, neon accents, clean fonts | Karan | 30 min | P1 |
| Add loading skeleton states so the dashboard doesn't flash blank | Karan | 20 min | P1 |

# 5.  Improvements & Suggestions vs. Original Plan

These are recommended changes and additions beyond the original brief. Some are critical fixes; others are product-level upgrades.

## 5.1  Critical Fixes

🔴 Fix 1: Blur must be Electron-level, not Extension-level The original plan mentions 'CSS blur via Extension.' An extension can only inject CSS into its own page context — it cannot blur system windows (VS Code, Figma, etc.). The blur must be applied as a transparent Electron BrowserWindow overlay that covers the entire display. This changes Dev A's implementation path significantly.

🔴 Fix 2: Chrome Extension must use chrome.alarms for heartbeat The original plan assumes the Extension runs persistently. MV3 Service Workers cannot use setInterval reliably — they are terminated after ~30s idle. Use chrome.alarms.create() for the focus-session heartbeat. This is a critical reliability fix.

🔴 Fix 3: Three.js plant rendering must use InstancedMesh Spawning individual Mesh objects per plant will cause severe FPS drops after 30-40 plants. Use Three.js InstancedMesh to batch all instances of the same plant type into a single draw call. This affects Karan's garden implementation.

## 5.2  Product Improvements

🟡 Improvement 1: Add a 'Focus Mode' selector Let users define what counts as 'Focus' for them. A designer's focus apps are different from a developer's. Provide 3 preset profiles (Dev, Designer, Writer) and a custom mode. This takes ~45 minutes and dramatically increases the product's perceived maturity.

🟡 Improvement 2: Onboarding flow The original plan has no onboarding. A first-run wizard (3 screens: Choose Profile → Name your Duck → Invite a teammate) takes 1-2 hours but is crucial for the product feeling like a real app rather than a hackathon demo.

🟡 Improvement 3: Roast quality — use context-aware prompting Instead of a generic roast, pass the Gemini API the distraction category, the current streak broken, and the time of day for more targeted roasts. E.g.: 'User was on a 45-minute streak, broke it at 2pm watching YouTube gaming content.' This costs the same API call but produces significantly funnier output.

🟢 Improvement 4: Duck should react to cursor proximity at all times Inspired by Desktop Gremlin — even in Idle state, the Duck should subtly follow the cursor (with a lag/spring animation) and tilt its head toward it. This makes the Duck feel alive 100% of the time, not just when chaos triggers. Estimated: 30 minutes for Dev A.

🟢 Improvement 5: Weekly Garden summary email or notification Every Monday, send a push notification: 'Last week you grew 12 plants and your garden is thriving 🌱' or 'Your garden lost 3 plants this week. The Duck is disappointed.' This is a retention mechanic that requires ~2 hours of backend work post-hackathon.

## 5.3  What to Cut from the MVP

Scope creep kills hackathon projects. The following features from the original brief should be explicitly deprioritized:

- Multiple Duck skins (P2 — unless Karan finishes all P0/P1 tasks early)

- Custom domain block list management UI (hardcode the list for the hackathon)

- User authentication with JWT / OAuth (use a simple username-based session for the hackathon — auth is a time sink)

- Mobile dashboard (Electron + Next.js desktop is enough for the demo)

- Payment/subscription flow (describe the pricing model in the pitch, don't build it)

# 6.  Demo Script (Hackathon Presentation)

Follow this script exactly during the demo. Practice it at least twice in the final hour.

| # | Segment | What You Show | What You Say |
| --- | --- | --- | --- |
| 1 | The Hook (15s) | Blank screen with Duck sitting idle on desktop over VS Code | 'This is the Duck. He lives on your desktop. He's watching you.' |
| 2 | The Problem (20s) | Show distraction stats — avg 3hrs/day lost | 'We lose 3 hours a day to distraction. Every app has failed to fix it because they don't fight back.' |
| 3 | The Stick (30s) | Open YouTube → Watch Duck go Chaos → Blur activates → Roast fires | 'The Duck sees everything. The moment you drift, he comes for you.' |
| 4 | The Carrot (20s) | Switch to VS Code → Duck calms → Show garden growing a plant live | 'But when you focus? Your garden grows. Your work builds something real.' |
| 5 | Squad (30s) | Trigger Ghost Duck from second laptop on stage — audience watches it hit | 'And if a teammate catches you slacking... they can send this.' |
| 6 | The Close (15s) | Show dashboard with analytics and full garden | 'Quack-Focus. Your focus, gamified. Your team, accountable. Your attention, defended.' |

⚡ Demo Day Fallback Plan If Socket.io is flaky on venue WiFi: pre-trigger the Ghost Duck via a hardcoded keyboard shortcut. If the Electron app crashes: have the 90-second screen recording ready. Never demo something you can't control — always have a fallback.

# 7.  Resources & Reference Links

## Key Libraries

- Three.js (r3f in Next.js): https://docs.pmnd.rs/react-three-fiber

- Electron Docs (transparent windows): https://www.electronjs.org/docs/latest/api/browser-window

- Chrome MV3 (chrome.alarms): https://developer.chrome.com/docs/extensions/reference/alarms

- Socket.io: https://socket.io/docs/v4

- Gemini API (Google AI Studio): https://ai.google.dev

- Mongoose (MongoDB ODM): https://mongoosejs.com

## 3D Asset Notes

- Duck GLB states needed: idle, walk, bite, water, eat, ghost — export all from same Blender rig

- Keep each GLB under 2MB for fast Electron load — decimate geometry if needed

- Confirm Three.js AnimationMixer handles all clips from a single GLB — it does if all actions are in one file

🦆 Final Note The Duck is the product. Every technical decision should serve the question: 'Does this make the Duck feel more alive?' If it doesn't, it's a P2. Ship the Duck. Ship the roast. Ship the Ghost Duck. That's the product.

Quack-Focus — Internal Build Documentation v1.0 — Good luck. 🦆